## Sheet1
# | Tasks | time ( days ) | note
1 | Database designe | 6
2 | Working with image hosting | 1
3 | Catche mechanism | 1
4 | Minitfy resources | cannot specify time ( work with progress )
5 | High speed XHR + JSON | cannot specify time ( work with progress )
6 | Optimize database query + fine tuning | 2
Fontend
7 | User registration + login | 1
8 | listing product + serching | 10
9 | product details page | 3
10 | Ebay and Amazon Store integration | 5
11 | Helper Chat Application | 1
12 | SEO Optimization | cannot specify time ( work with progress )
13 | Social Media integration | 1
14 | login with facebook | 1
15 | Product display method | 1
16 | Custom Computer Build | 3
17 | Prebuilt Computers | 1
18 | Shipping Cost calculation | 2
19 | User Account details | 3
20 | Payment options | 3
21 | Cart application | 3
22 | Order cration | 2
| Calculation for order | 3
23 | Site setup | 1
Backend
1 | User management | 2
2 | Role management | 1
3 | Order management | 3
4 | Dashboard | 2
5 | Product Management | cannot specify time ( work with progress ) (6)
6 | Supplier Management | 4
7 | Ebay + Amazon management | 5
8 | Super admin Management | 1
| Total | 78
cannot specify time ( work with progress )--> this point cannot be included in milestone